## Gantt (hidden)
Smart Waste Collection Scheduling System
Gantt Chart
Project start | 2026-09-22 |  | Calendar days | 80
Task | Start | Finish | Days | Priority | Task | Offset | High | Medium
System Request | 2026-09-22 | 2026-09-23 | 2 | High | Implementation | 56 | 24 | 0
Feasibility Study | 2026-09-24 | 2026-09-27 | 4 | High | Design | 36 | 20 | 0
PERT and Gantt Chart | 2026-09-28 | 2026-10-03 | 6 | High | Normalization | 32 | 4 | 0
Interview | 2026-10-04 | 2026-10-06 | 3 | Medium | Entity Relationship | 28 | 4 | 0
Questionnaire | 2026-10-07 | 2026-10-09 | 3 | Medium | Process Specification | 24 | 4 | 0
Data Flow Diagram | 2026-10-10 | 2026-10-13 | 4 | High | Data Store | 22 | 2 | 0
Data Store | 2026-10-14 | 2026-10-15 | 2 | High | Data Flow Diagram | 18 | 4 | 0
Process Specification | 2026-10-16 | 2026-10-19 | 4 | High | Questionnaire | 15 | 0 | 3
Entity Relationship | 2026-10-20 | 2026-10-23 | 4 | High | Interview | 12 | 0 | 3
Normalization | 2026-10-24 | 2026-10-27 | 4 | High | PERT and Gantt Chart | 6 | 6 | 0
Design | 2026-10-28 | 2026-11-16 | 20 | High | Feasibility Study | 2 | 4 | 0
Implementation | 2026-11-17 | 2026-12-10 | 24 | High | System Request | 0 | 2 | 0